## Sheet1
Tracks | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Remarks
Define problem statement | 2020-01-23 | 2020-01-24 |  |  | Done
Data identification-with the define of dependent and independent variables | 2020-01-28 | 2020-02-07
Collect the require data from different sources | 2020-02-10 | 2020-02-14
Exploratory Data Analysis - Data cleaning, data mining, data exploration,patter reconnization, visualization etc. | 2020-02-17 | 2020-02-28
Make the data in strucutred format and ready to use for next steps | 2020-03-02 | 2020-03-03
Modeling - Ensemble | 2020-03-04 | 2020-03-13
Measure model performance (metrics) | 2020-03-04 | 2020-03-13
Business Intellengence | 2020-03-16 | 2020-03-17
Storytelling | 2020-03-18 | 2020-03-19

## Sheet2
Customer historical data
Action Series
| SMS | 1 |  |  | Segment | Credit history | Occuption | Account details | Frequency of deliquency | Risk category
| Email | 2
| Chatbot | 3 |  |  | Self cure |  | salaried |  |  | Very low
| Telecall | 4 |  |  | B |  | self employed |  |  | low
| Field | 5 |  |  | C |  | .. |  |  | medium
| Legal | 6 |  |  | D |  | .. |  |  | high
very high
| Willing to pay |  | Paid
|  |  | Yes | Payment happened on what? |  |  | and for which specific risk category
No
..
..
1. Customer histrocial data and the deliquency frequency reocrods for different accounts
2 Based on the point numbder 1, define the customer segment
3. The action series applied on the accounts and based on the parameter set for Risk category.
4. Which specific action successful for customer willing to pay
5. When actual customer pay the payment vis a vis of duration difference of willing to pay.